## Read Me
SECURE BY DESIGN TRAINING SAMPLE - NOT AN OFFICIAL FORM. For instruction and practice with fictional data only.
Plan of Action and Milestones (POA&M) - training sample
What it is | The POA&M records each weakness the assessment or monitoring finds and the plan to correct it. The AO uses it to monitor progress (JSIG RMF Step 5, Task 5-1).
JSIG minimum | For each task: the tasks to be accomplished (with a recommendation to complete them before or after implementation), the resources required, the milestones including percentage completed, and the scheduled completion dates for the milestones.
Columns | Field names follow CDSE's public POA&M Job Aid. One row per milestone: repeat the POA&M ID on each milestone row of the same weakness.
Risk | Severity, likelihood, impact and residual risk use the NIST SP 800-30 scale (Very Low to Very High), the same scale as the Risk Assessment Report.
Grey cells | Supplied data. Leave as is.
Yellow cells | Fill these in for your (fictional) system.
Green row | A worked example with fictional values, showing the expected format. Replace or delete it.
Sources | DoD Joint SAP Implementation Guide, 11 April 2016, Task 5-1 (dcsa.mil); CDSE Plan of Action and Milestones Job Aid (cdse.edu); NIST SP 800-53 Rev. 5 CA-5; NIST SP 800-30 Rev. 1.
Notice | Written by Secure By Design for training. Not an official form.

## POA&M
SECURE BY DESIGN TRAINING SAMPLE - NOT AN OFFICIAL FORM. For instruction and practice with fictional data only.
Plan of Action and Milestones (POA&M)
POA&M ID | Control vulnerability description | Controls / APs | Security checks (e.g., STIG rule or CVE) | Office / org | Resources required | Scheduled completion date | Milestone ID | Milestone description | Milestone % complete | Milestone scheduled completion date | Milestone status | POA&M status | Identification source | Identification source details | Raw severity | Mitigations | Severity | Relevance of threat | Likelihood | Impact | Impact description | Residual risk level | Recommendations | Completion date | Comments
POAM-001 | Two workstation images allow removable-media write access, contrary to the SSP. | MP-7 | Windows 11 STIG rule (removable storage) | SBD IT Operations | 4 admin hours; GPO change window | 2026-12-15 | 1 | Update the workstation GPO to deny write access to removable storage | 50% | 2026-11-15 | Ongoing | Ongoing | Security control assessment | SAR finding 7, 2026-10-01 | Moderate | Media use logged by the ISSO; users briefed | Moderate | Moderate | Low | Moderate | Unauthorized copying of data to removable media | Low | Apply the GPO and rescan with SCC |  | Fictional example
POAM-001 |  | MP-7 |  |  |  | 2026-12-15 | 2 | Rescan both images with SCC and attach the results | 0% | 2026-12-15 | Ongoing | Ongoing | [12 empty] | Second milestone of POAM-001

## Summary
SECURE BY DESIGN TRAINING SAMPLE - NOT AN OFFICIAL FORM. For instruction and practice with fictional data only.
POA&M summary
Measure | Value
Milestone rows | 2
Milestones Not started | 0
Milestones Ongoing | 2
Milestones Completed | 0
Milestones Delayed | 0
Residual risk Very Low | 0
Residual risk Low | 1
Residual risk Moderate | 0
Residual risk High | 0
Residual risk Very High | 0
Average milestone % complete | 25%